## Dashboard
Dashboard_
Count of Coding Status |  |  |  | Testing Status
Project_Type | Team | Coding Status | Idea Name | Complete | Grand Total
ENHANCEMENT | CARGO READINESS | Complete | AUTOMATE EMAIL NOTIFICATION SENT TO CUSTOMERS | 1 | 1
|  |  | CARGO READINESS - CHASING CUSTOMERS | 1 | 1
| DG | Complete | IMDG AUDIT FILE 8.35 VERSION_17 28 DEC | 1 | 1
|  |  | RE: DG CARGO AUDIT FILE | 1 | 1
| Claim | Complete | Daily Productivity Count | 2 | 2
MAINTAINANCE | DG | Complete | TAT AUTOMATION _REPORT | 1 | 1
NEW PROJECT | CARGO READINESS | Complete | AUTOMATE EMAIL NOTIFICATION SENT TO CUSTOMERS | 1 | 1
|  |  | AUTOMATE JOURNEY LEG RFI EMAILS | 1 | 1
|  |  | IDENTIFY BOOKING PARTY NAME | 1 | 1
|  |  | LARA PML VS TERMINAL LOAD LIST COMPARISON | 1 | 1
| PCR | Complete | SUMMARIZATION OF MONITORING AND SHIPMANAGER COUNT | 1 | 1
|  |  | TRANSHIPMENT_LCR11.1 REPORT_EXCEL FILE CREATION | 1 | 1
|  |  | WEEKLY REPORT FORMAT & WEEKLY REPORT PPT CREATION | 1 | 1
| Claim | Complete | Request for creating a macro | 1 | 1
Grand Total |  |  |  | 15 | 15
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Work History
Maersk India (ssc) Pvt Ltd.
Areas : | 1.Sales support, Rates quotation to customers, Rates integration into system.
CMA CGM GBS INDIA
Areas : | 1.Service Contract
2.Tender
3.IFF (International fright forwarding)
4.VGM(Varified gross mass)
Kuehne-Nagel India Pvt Ltd | 1.Sea rates filling into system

## Project_List Operations
Project_Type | Team | Idea Name | Idea Description | Tools_used | Idea Type | Project Timeline | Start Date | Complete Date | Requester_user | Coding Status | Testing Status | Current Status | Comment | Remarks(Managers Comments) | Benefits achieved
MAINTAINANCE | DG | TAT AUTOMATION _REPORT | - | EXCEL,VBA | Simple | 4-6 Hrs | 2021-12-21 | 2021-12-22 | GOSAVI AMIT | Complete | Complete | Complete |  |  | Time Saving
NEW PROJECT | VGM | VGM AUTOMATION-MISSING VGM CHASER REPORT | DURING CONTIGENCY SITUATION OR VIRA TOOL HAVING ISSUE PRODUCTION OF MISSING CHASER REPORT WILL NOT STOP | PYTHON, EXCEL | Complex | 4-5 days | 2022-04-19 | - | MAYUR NIMBALKAR | Work In Progrees | Work In Progrees | Work In Progrees |  |  | Time Saving
NEW PROJECT | PCR | WEEKLY REPORT FORMAT & WEEKLY REPORT PPT CREATION | - | EXCEL,VBA | Complex | 6-8 days | 2022-02-25 15:59 | 2022-03-01 21:28 | PRAMOD PATIL | Complete | Complete | Complete |  |  | Time Saving & Accuracy
ENHANCEMENT | CARGO READINESS | CARGO READINESS - CHASING CUSTOMERS | ENHANCE THE EXISTING MACRO AS IT TAKES MORE TIME TO SEND EMAILS TO CUSTOMERS FROM LAPTOP AS COMPARED TO OFFICE DESKTOP | EXCEL,VBA | Simple | 4-6 Hrs | - | - | NIDHEESH LAKSHMANAN | Complete | Complete | Complete |  |  | Time Saving
ENHANCEMENT | DG | IMDG AUDIT FILE 8.35 VERSION_17 28 DEC | - | EXCEL,VBA | Simple | 4-6 Hrs | - | - | SALVI SAMEER | Complete | Complete | Complete |  |  | Accuracy
NEW PROJECT | OPS ASSISTANCE | ANTWERP GATEWAY 1700 | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | 2021-12-23 | 2021-12-25 | LEO RODRIGUES | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | ANTWERP PSA Q913 | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | 2021-12-25 | 2021-12-26 | LEO RODRIGUES | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | ANTWERP PSA TERMINAL 869 | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | 2021-12-26 | 2021-12-28 | LEO RODRIGUES | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | HTTPS://WWW.IAMCONNECTED.EU/ | - | PYTHON, EXCEL | Complex |  | - | - | AMBETH | Pending | Pending | Pending |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | ROTTERDAM WORLD GATEWAY TERMINAL | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | 2021-12-29 | 2021-12-30 | LEO RODRIGUES | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | NETHERLAND DE: EUROGATE | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | 2021-12-31 | 2022-01-04 | LEO RODRIGUES | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | (BREMERHAVEN, DE) CMA3PF | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 4-5 days | 2022-01-05 | 2022-01-12 | LEO RODRIGUES | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | (HAMBURG, DE) BALTIC SHUTTLE SERVICE E | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 4-5 days | 2022-01-12 | 2022-01-19 | LEO RODRIGUES | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | (LUBECK, DE) CONTAINERSHIPS INTRA BALT SERVICE | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | 2022-01-19 | 2022-01-21 | LEO RODRIGUES | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | (WILHELMSHAVEN, DE) BALTIC SHUTTLE SERVICE D | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | 2022-01-22 | 2022-01-22 | LEO RODRIGUES | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | LONDON GATEWAY | - | PYTHON, EXCEL | Complex | 1-2 days | 2022-01-23 | 2022-01-25 | LEO RODRIGUES | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | FELIXSTOWE | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | 2022-01-27 | 2022-01-27 | LEO RODRIGUES | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | SOUTHAMPTON | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | 2022-01-25 | 2022-01-27 | LEO RODRIGUES | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | HTTP://EPORT.SCCTCN.COM/QUERY/VESSELSCHEDULE | - | PYTHON, EXCEL | Complex | 4-5 days | - | - | AMBETH | Pending | Pending | Pending | SHEKOU |  | Time Saving & Accuracy
NEW PROJECT | PCR | BREAK BULK REPORT FROM LARA SCREEN | - | EXCEL,VBA | Complex |  | - | - | PRAMOD PATIL | Pending | Pending | Pending |  | Under Discussion | Time Saving & Accuracy
ENHANCEMENT | DG | RE: DG CARGO AUDIT FILE | - | EXCEL,VBA | Simple | 4-6 Hrs | 2022-01-13 | 2022-01-17 | MANOJ YADAV | Complete | Complete | Complete |  |  | Accuracy
NEW PROJECT | OPS ASSISTANCE | ONE | - | PYTHON, EXCEL | Complex | 1-2 days | 2021-12-22 | 2021-12-24 | LEO RODRIGUES | Complete | Under Testing | Under Testing | PARTNERS VESSELS |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | COSCO | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | 2021-12-24 | 2021-12-28 | LEO RODRIGUES | Complete | Under Testing | Under Testing | PARTNERS VESSELS |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | HAPAG LLOYD | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | 2021-02-02 | 2021-02-03 | LEO RODRIGUES | Complete | Under Testing | Under Testing | PARTNERS VESSELS |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | MAERSK | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | 2021-12-31 | 2022-01-03 | LEO RODRIGUES | Complete | Under Testing | Under Testing | PARTNERS VESSELS |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | CMA CGM | - | PYTHON, EXCEL | Complex | 1-2 days | 2022-01-03 | 2022-01-06 | LEO RODRIGUES | Complete | Under Testing | Under Testing | PARTNERS VESSELS |  | Time Saving & Accuracy
NEW PROJECT | PCR | AUTO APPROVAL OF PCR AFTER CLOSING | PCR'S HAVE 7 TABS WHICH SHOULD GET AUTOAPPROVED AFTER 24-36 HRS | WIN- AUTAMATION TOOL | Complex |  | - | - | RAVIKIRAN/ PRAMOD | Pending | Pending | Pending |  |  | Time Saving & Accuracy
NEW PROJECT | PCR | AUTO REFUSAL OF PCR AFTER RECEIVING MAIL | SHOULD READ MAILS RECEIVED FROM AGENCIES AND REFUSED REQUESTED TAB | WIN- AUTAMATION TOOL | Complex |  | - | - | RAVIKIRAN/ PRAMOD | Pending | Pending | Pending |  |  | Time Saving & Accuracy
NEW PROJECT | PCR | TRANSHIPMENT_LCR11.1 REPORT_EXCEL FILE CREATION | - | PYTHON, EXCEL | Simple | 3-4 days | 2022-02-01 | 2022-02-04 | SACHIN THAKUR | Complete | Complete | Complete | 1st testing phase completed |  | Time Saving & Accuracy
NEW PROJECT | CARGO READINESS | AUTOMATE EMAIL NOTIFICATION SENT TO CUSTOMERS | AUTOMATICALLY SENDING EMAIL NOTIFICATION TO CUSTOMERS AFTER CANCELLING THE BOOKING. | PYTHON, EXCEL | Complex | 2-3 days | - | - | NIDHEESH LAKSHMANAN | Complete | Complete | Complete |  |  | Time Saving
NEW PROJECT | CARGO READINESS | AUTOMATE JOURNEY LEG RFI EMAILS | AUTOMATE RFI EMAILS SENT TO CARGO CARE TEAM | PYTHON, EXCEL |  | 2-3 days | - | - | NIDHEESH LAKSHMANAN | Complete | Complete | Complete |  |  | Time Saving
ENHANCEMENT | OPS ASSISTANCE | AUTO CHANGE ETD IN BAYPLAN TRACKER | AUTO ETD CHANGE IN BP TRACKER AS PER LARA VOYAGE SCHEDULE | EXCEL,VBA | Complex |  | - | - | RAVINDRA POOJARY | Pending | Pending | Pending |  | Under Discussion | Time Saving & Accuracy
NEW PROJECT | PCR | WEB PAGE REFRESH | PORTNET NEEDS TO REFRESHED TO KEEP ACTIVE SESSION | PYTHON, EXCEL | Simple | - | - | - | PRAMOD PATIL | Pending | Pending | Pending |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | BAY PLAN ETD DATE CHECK MACRO | TO FETCH THE ETD OF ALL THE VESSEL SO THAT MANUAL EFFORTS ARE STOPPPED | EXCEL,VBA | Complex |  | - | - | Kishore | Pending | Pending | Pending |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | BAYPLAN TRACKER | EXCEL TRACKER | EXCEL,VBA | Complex |  | - | - | RAVINDRA POOJARY | Pending | Pending | Pending |  |  | Time Saving & Accuracy
NEW PROJECT | CARGO READINESS | IDENTIFY BOOKING PARTY NAME | IDENTIFY BOOKING PARTY NAME FOR BOOKINGS WHERE THE BOOKING PARTY NAME DID NOT GENERATE FROM LARA CARGO | EXCEL,VBA | Simple | 1-2 days | - | - | NIDHEESH LAKSHMANAN | Complete | Complete | Complete |  |  | Time Saving
NEW PROJECT | CARGO READINESS | LARA PML VS TERMINAL LOAD LIST COMPARISON | COMPARE AND PROVIDE OUTPUT IN THE DESIRED FORMAT FOR CHASING CUSTOMERS OR AGENCY WHILE PERFORMING PRE & POST VESSEL CLEAN UP CHECKS | PYTHON, EXCEL | Complex | 2-3 days | - | - | NIDHEESH LAKSHMANAN | Complete | Complete | Complete |  |  | Time Saving
ENHANCEMENT | CARGO READINESS | AUTOMATE EMAIL NOTIFICATION SENT TO CUSTOMERS | HIGHLIGHT THE NOTE SECTION WITH CONTAINER NUMBER PLACE CHANGES. | PYTHON, EXCEL | Simple | 2-3 days | - | - | NIDHEESH LAKSHMANAN | Complete | Complete | Complete |  |  | Time Saving
ENHANCEMENT | CARGO READINESS | LARA PML VS TERMINAL LOAD LIST COMPARISON | NEED TO ADD MORE CRITERIA | PYTHON, EXCEL | Complex | 2-3 days | - | - | NIDHEESH LAKSHMANAN | Complete | Under Testing | Under Testing | AU COMPARISON |  | Time Saving & Accuracy
NEW PROJECT | PCR | SUMMARIZATION OF MONITORING AND SHIPMANAGER COUNT | - | EXCEL,VBA | Simple | 4-6 Hrs | 2022-05-19 | 2022-05-19 | PRAMOD PATIL | Complete | Complete | Complete |  |  | Time Saving & Accuracy
NEW PROJECT | DDSM | Invoice PDF Merger | Automation for merging the multiple pdf into single pdf file | PYTHON, EXCEL | Complex | - | - |  | Saddam | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | DDSM | TBI automation | Automation to TBI report (Detention & Demurrage) | PYTHON, EXCEL | Complex | - | - |  | Saddam | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | BAY PLANE | BAY PLAN Reminder automation | Start to End auto process throught tool. | EXCEL,VBA,Python | Complex | - | - | - | Kishore | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | Outlook mail Sent item details | To get count of mail, being send in days with all specific details. | PYTHON, EXCEL | Complex |  |  |  | Suraj | Pending | Pending | Pending |  |  | Time Saving & Accuracy
NEW PROJECT | PCR | Transhipment process Auto_Missing Voyage | Missing Voyage | PYTHON, EXCEL | Simple | 3-4 days | - | - | SACHIN THAKUR | Complete | Complete | Complete |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | CNC DPS upload | To arrange in orderwise with specific vessel details into excel file. | PYTHON, EXCEL | - | - | - | - | Rupesh, John | Pending | Pending | Pending |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | OOG Tracker | - | PYTHON, EXCEL | Complex | - | - | - | LEO RODRIGUES | Pending | Pending | Pending |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | LTS Creation throught macro. | LTS_Data migration( with multiple condition) from various resources like PDF and excel.. | PYTHON,EXCEL, VBA | Complex | - | - | - | Rupesh | Pending | Pending | Pending |  |  | Time Saving & Accuracy
NEW PROJECT | CARGO READINESS | Language Translation throught tools i/o google. | Language Translation throught tools i/o google. | PYTHON,EXCEL | Complex | - | - | - | Paul Carvalido | Pending | Pending | Pending |  |  | Time Saving
ENHANCEMENT | OPS ASSISTANCE | COSCO_CMA Comparison | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | - | - | LEO RODRIGUES | Work In Progrees | Work In Progrees | Work In Progrees | Comparison |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | TAT Report automation | TAT Percentage would be calculated automatically considering existing data in allocation sheets | PYTHON, EXCEL | Complex | 1-2 days | - | - | Suraj | Pending | Pending | Pending |  |  | Time Saving & Accuracy | 15min
NEW PROJECT | OPS ASSISTANCE | Weekly Volume automation | To Collect all simulation and amendment data from sharepoint and collating into common table format | PYTHON, EXCEL | Complex | 1-2 days | - | - | Suraj | Pending | Pending | Pending |  |  | Time Saving & Accuracy | 20min
NEW PROJECT | Claim | Request for creating a macro | Get capture the users productivity (In terms of count of mail) on daily basis throught email sent. | EXCEL/VBA | Simple | 5 hrs | 44589 | 44592 | Kumar Manish | Complete | Complete | Complete |  |  | Accuracy
ENHANCEMENT | Claim | Daily Productivity Count | Thank you and would like to confirm that the macro has pulled the data from inbox and is working. However check if it is possible to get the result basis BL no. and date sent against each claim handler. | EXCEL/VBA | Simple | 5 hrs | 44593 | 44593 | Kumar Manish | Complete | Complete | Complete |  |  | Accuracy
ENHANCEMENT | Claim | Daily Productivity Count | Get users email count based on customise date & Fresh¦Old Data along with generic mail box | EXCEL/VBA | Simple | 6 hrs | 44599 | 44601 | Kumar Manish | Complete | Complete | Complete |  |  | Accuracy
NEW PROJECT | OOG -OPS ASSISTANCE | Reminder mail for approval (OOG cargo) | Send mails for approval regarding OOG cargo( with chain mailling) | PYTHON, EXCEL | Complex | 1-2 days | - | - | LEO RODRIGUES | Complete | Complete | Complete |  |  | Time Saving & Accuracy
ENHANCEMENT | Cargo Ops/Transhipment | Transhipment process Auto_Missing Voyage | Need to add first POL in subject line | PYTHON, EXCEL | Simple | 1-2 days | - | - | SACHIN THAKUR | Complete | Complete | Complete |  |  | Time Saving & Accuracy
NEW PROJECT | OOG -OPS ASSISTANCE | reminder process for COD | Sending reminder to partner manually which is time consuming | PYTHON, EXCEL | Complex | 4-5 hrs | - | - | Jessica GOMES | Complete | Complete | Complete |  |  | Time Saving & Accuracy
NEW PROJECT | CARGO READINESS | SERVICE NAME extraction | - | EXCEL/VBA | Simple | 4 hrs | - | - | Deep Tripathi | Complete | Complete | Complete
NEW PROJECT | DDSM | Extraction of PDF | Extraction of PDF (BL & Invoice) from outlook | PYTHON, EXCEL | Complex | - | - | - | Prince | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | Transition | Auto send report to respective person | Auto send report to respective person | PYTHON, EXCEL | Complex | 1-2 days | - | - | Sharad karkera | Complete | Under Testing
MAINTAINANCE | CARGO READINESS | NO activity bug | bug: due to outlook error ( server not find) | EXCEL/VBA | Simple | 4 hrs | - | - | Deep Tripathi | Complete | Complete | Complete
NEW PROJECT | OPS ASSISTANCE | [7 empty] | Rupesh | Pending
NEW PROJECT | OPS ASSISTANCE | [7 empty] | Joh Pillai | Pending
NEW PROJECT | PCR | [7 empty] | Shaikh | Pending
NEW PROJECT | CARGO READINESS | [7 empty] | Ambethe | Pending
NEW PROJECT | Cargo Ops/Transhipment | VGM missing _ Transhipment | VGM missing _ Transhipment | PYTHON, EXCEL | Simple | 3-4 days | - | - | SACHIN THAKUR | Work In Progrees | Work In Progrees | Work In Progrees
NEW PROJECT | DG | Cxml to xlsx and comparision | Cxml to xlsx and comparision | PYTHON, EXCEL | Simple | 1-2 days | - | - | MANOJ YADAV | Complete | Work In Progrees | Work In Progrees

## Project_List Others Dept.
Project_Type | Team | Idea Name | Idea Description | Tools_used | Idea Type | Project Timeline | Start Date | Complete Date | Requester_user | Coding Status | Testing Status | Status | Remarks(Managers Comments) | Benefits achieved
to be updated by delivery Team | to be updated by delivery Team | to be updated by delivery Team | to be updated by delivery Team | to be updated by Akhilesh | to be updated by Akhilesh | to be updated by Akhilesh | to be updated by Akhilesh | to be updated by Akhilesh | to be updated by delivery team | to be updated by Akhilesh | to be updated by Akhilesh | to be updated by Akhilesh | to be updated by delivery team | to be updated by delivery team
ENHANCEMENT | SVC_ | Daily Count : With Audit status | - | EXCEL/VBA | Simple | 5 hrs | 2021-12-21 | 2021-12-22 | Arun Mukannath | Complete | Complete | Complete |  | Time Saving & Accuracy
NEW PROJECT | IT team Thane | Auto extract console data and pull screen shot of command prompt | Auto extract console data and pull screen shot of command prompt | Python¦BAT | Complex | 5 hrs | 2022-02-15 | 2022-02-15 | Neeraj Jha | Complete | Complete | Complete |  | Time Saving
NEW PROJECT | SVC_ | To Extract the SVC contract details from LARA Mirror | Based on Contract number and Amendment number , get entire details `` | ExCEL/VBA | Simple | 4.30 hrs | 2022-02-16 | 2022-02-16 | Preetam M | Complete | Complete | Complete |  | Time Saving & Accuracy
ENHANCEMENT | SVC_ | Port Group extraction | Additionally, extract Ports of respective groups | ExCEL/VBA | Simple | 5 hrs | 2022-02-16 | 2022-02-16 | Preetam M | Complete | Complete | Complete |  | Time Saving & Accuracy
NEW PROJECT | Tender_Integration | Merge, Dry, Reefer D & D Consolidation | - | ExCEL/VBA | Complex | 3-4 Days | 2022-03-08 | 2022-03-15 | Navid M | Complete | Complete | Complete |  | Time Saving & Accuracy
NEW PROJECT | HR_Photo_dist. | Dist. Official photo to resp. emplyee | - | Python¦Excel | Complex | 3-4 Days | 2022-06-12 | 2022-07-21 | Savio Johanathan | Complete | Complete | Complete |  | Time Saving & Accuracy
ENHANCEMENT | SVC_ | Qspot mail template | - | ExCEL/VBA | Simple | 5 hrs | 2022-06-24 | 2022-06-24 | Preetam M | Complete | Complete | Complete |  | Time Saving & Accuracy
ENHANCEMENT | SVC_ | DDSM_column addition | - | ExCEL/VBA | Simple | 5 hrs | 2022-06-24 | 2022-06-24 | Preetam M | Complete | Complete | Complete |  | Time Saving & Accuracy
NEW PROJECT | SVC_ | DTHC- China | - | ExCEL/VBA | Simple | 5 hrs | - | - | Sameer karbelkar | Complete | Work In Progrees | Work In Progrees |  | Time Saving & Accuracy
NEW PROJECT | Tender | Consolidation of multiple appendix tabs | consolidation of appendix data with charges | ExCEL/VBA | Simple | 5 hrs | - | - | Arvind / Lokesh | Complete | Work In Progrees | Work In Progrees |  | Time Saving & Accuracy
NEW PROJECT | Booking Team | Email notification with different type of template & LARA details extraction | Auto extract details from LARA and send notification basis on different different type of template | Python¦ExCEL/VBA | Simple | 10-14 days | - | - | Balaganesh |  | Work In Progrees | Work In Progrees |  | Time Saving & Accuracy
NEW PROJECT | Booking Team | [7 empty] | Devendra | Pending