## Dashboard (hidden)
Dashboard
Count of Coding Status |  |  |  | Testing Status
Project_Type | Team | Coding Status | Idea Name | Complete | Pending | Under Testing | Grand Total
NEW PROJECT | CARGO READINESS | Complete | AUTOMATE EMAIL NOTIFICATION SENT TO CUSTOMERS | 1 |  |  | 1
|  |  | AUTOMATE JOURNEY LEG RFI EMAILS | 1 |  |  | 1
|  |  | IDENTIFY BOOKING PARTY NAME | 1 |  |  | 1
|  |  | LARA PML VS TERMINAL LOAD LIST COMPARISON | 1 |  |  | 1
|  |  | SERVICE NAME extraction | 1 |  |  | 1
|  |  | Cargo Readiness - Automation of NDNL Cancellation Process |  |  | 1 | 1
| DG | Complete | Cxml to xlsx and comparision |  |  | 1 | 1
|  |  | Scanned PDF to be converted into an editable | 1 |  |  | 1
| OPS ASSISTANCE | Complete | (BREMERHAVEN, DE) CMA3PF |  |  | 1 | 1
|  |  | (HAMBURG, DE) BALTIC SHUTTLE SERVICE E |  |  | 1 | 1
|  |  | (LUBECK, DE) CONTAINERSHIPS INTRA BALT SERVICE |  |  | 1 | 1
|  |  | (WILHELMSHAVEN, DE) BALTIC SHUTTLE SERVICE D |  |  | 1 | 1
|  |  | ANTWERP GATEWAY 1700 |  |  | 1 | 1
|  |  | ANTWERP PSA Q913 |  |  | 1 | 1
|  |  | ANTWERP PSA TERMINAL 869 |  |  | 1 | 1
|  |  | CMA CGM |  |  | 1 | 1
|  |  | COSCO |  |  | 1 | 1
|  |  | FELIXSTOWE |  |  | 1 | 1
|  |  | HAPAG LLOYD |  |  | 1 | 1
|  |  | LONDON GATEWAY |  |  | 1 | 1
|  |  | MAERSK |  |  | 1 | 1
|  |  | NETHERLAND DE: EUROGATE |  |  | 1 | 1
|  |  | ONE |  |  | 1 | 1
|  |  | ROTTERDAM WORLD GATEWAY TERMINAL |  |  | 1 | 1
|  |  | SOUTHAMPTON |  |  | 1 | 1
|  |  | CNC DPS upload |  |  | 1 | 1
|  |  | OOG Tracker | 1 |  |  | 1
|  | Pending | HTTP://EPORT.SCCTCN.COM/QUERY/VESSELSCHEDULE |  | 1 |  | 1
|  |  | HTTPS://WWW.IAMCONNECTED.EU/ |  | 1 |  | 1
|  |  | Outlook mail Sent item details |  | 1 |  | 1
|  |  | LTS Creation throught macro. |  | 1 |  | 1
|  |  | Weekly Volume automation |  | 1 |  | 1
| PCR | Complete | SUMMARIZATION OF MONITORING AND SHIPMANAGER COUNT | 1 |  |  | 1
|  |  | TRANSHIPMENT_LCR11.1 REPORT_EXCEL FILE CREATION | 1 |  |  | 1
|  |  | WEEKLY REPORT FORMAT & WEEKLY REPORT PPT CREATION | 1 |  |  | 1
|  |  | Transhipment process Auto_Missing Voyage | 1 |  |  | 1
| VGM | Complete | VGM AUTOMATION-MISSING VGM CHASER REPORT |  |  | 1 | 1
|  |  | Edi_001 automation |  |  | 1 | 1
| DDSM | Complete | Invoice PDF Merger |  |  | 1 | 1
|  |  | TBI automation |  |  | 1 | 1
|  |  | Extraction of PDF |  |  | 1 | 1
| BAY PLANE | Complete | BAY PLAN Reminder automation |  |  | 1 | 1
| Claim | Complete | Request for creating a macro | 1 |  |  | 1
| OOG -OPS ASSISTANCE | Complete | Reminder mail for approval (OOG cargo) | 1 |  |  | 1
|  |  | reminder process for COD | 1 |  |  | 1
| Cargo Ops/Transhipment | Complete | VGM missing _ Transhipment | 1 |  |  | 1
|  |  | VGM missing _ Transhipment_06 & 11.0 | 1 |  |  | 1
Grand Total |  |  |  | 16 | 5 | 26 | 47
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Work History (hidden)
Maersk India (ssc) Pvt Ltd.
Areas : | 1.Sales support, Rates quotation to customers, Rates integration into system.
CMA CGM GBS INDIA
Areas : | 1.Service Contract
2.Tender
3.IFF (International fright forwarding)
4.VGM(Varified gross mass)
Kuehne-Nagel India Pvt Ltd | 1.Sea rates filling into system

## ProjectTaskList_2023
PROJECT TASK LIST
[11 empty] | Benefit_Time( In Min) | Benefit_Quality | Est.Hours | Act.Hours
[6 empty] | Project Start | 2022-12-20 |  |  | Totals | 15 | 2 | 30 | 23
TASK | PROJECT_TYPE | STATUS | TEAM | IDEA_DESCRIPTION | OWNER | TOOLS USED | PRIORITY | START | END | % COMPLETE | DONE | BENEFIT ( In Min) | EST. HOURS | ACTUAL HOURS | STATUS2 | APPRECIATION | COMMENT
PROJECT TITLE | [10 empty] | 0
DG_MYPAI | ENHANCEMENT | Completed | DG | To Change the mypai structure with calculation automatically | Palraj D | EXCEL¦VBA | LOW | 2022-12-19 | 2022-12-20 | 100% | 0 | Quality | 12 | 7 | Code_Completed
Terminal_Extraction | ENHANCEMENT | Pending | OPs_Support | COSCO - To avoid the task to extract vessel code for terminal automation | Leo R | EXCEL¦PYTHON¦SELENIUM | MEDIUM | 2022-12-20 |  | 60% | 0 |  |  |  | In Progress
NDNL - US CR | MAINTENANCE | Pending | Cargo Rediness | RE: Automation tool : No Doc No Load - US CR Process | Deep T | EXCEL¦PYTHON | MEDIUM |  |  |  | 0 |  |  |  | Not Started
Weekly_Consolidation_Report | NEW PROJECT | Completed | Claim | To consolidate the multiple weekly report in single file | Ramesh K | EXCEL¦PYTHON | HIGH | 2022-12-21 | 2022-12-22 | 100% | 1 | 15 | 18 | 16 | Code_Completed | Kudos to your prompt response Akhilesh.
Dubai Transhipment automation_Part A | NEW PROJECT | Pending | Transhipment | Last pol Edi and LARA PML, analysis, clearing descripancy | Sachin T | [5 empty] | 0
Dubai Transhipment automation_Part C | NEW PROJECT | Pending | Transhipment | Remove AEJAL cargo from cuscade file | Sachin T | [5 empty] | 0
Dubai Transhipment automation_Part B | NEW PROJECT | Pending | Transhipment | Creating manual excel summary, to send load team | Sachin T | [5 empty] | 0
Missing vessels VGM on Transhipment | ENHANCEMENT | Completed | Transhipment | Remove XRX | Sachin T | EXCEL¦PYTHON | LOW | - | - | 100% | 1 | Quality | - | - | Code_Completed | The VGM tool is working successfully. Thank you for your continuous support.
BAY PLAN Reminder automation | ENHANCEMENT | Pending | OPs_Support | - | Kishore | [5 empty] | 0
Lara Pml Vs Terminal Load List Comparison | ENHANCEMENT | Pending | Cargo Rediness | - | Nedheesh | [5 empty] | 0
Cargo Readiness - Automation Of Ndnl Cancellation Process | NEW PROJECT | Pending | Cargo Rediness | Automate the entire process( data process + mail distributing to Bot) | Deep T | [5 empty] | 0
CNC DPS upload | ENHANCEMENT | In-Progress | OPs_Support | To arrange in orderwise with specific vessel details into excel file. | Rupesh | [5 empty] | 0
LTS Creation throught macro. | NEW PROJECT | Pending | OPs_Support | LTS_Data migration( with multiple condition) from various resources like PDF and excel. | Rupesh | [5 empty] | 0
VGM automation | ENHANCEMENT | Pending | VGM | To improve the time taken by tool. | Manoj Y | [5 empty] | 0
DG_Outlook_mail auto assignment to user | NEW PROJECT | Pending | DG | To track each mail and auto assigned to user by tools | Havesh K | [5 empty] | 0
File follow up auto mail (pilot project with small countries) | NEW PROJECT | Pending | PCR | - | Ravikiran M | [5 empty] | 0
PCR approval | NEW PROJECT | Pending | PCR | - | Ravikiran M | [5 empty] | 0
PCR PDF report auto mail to Agency after PCR Closing (India and Germany) | NEW PROJECT | Pending | PCR | - | Ravikiran M | [5 empty] | 0
Dashboard from CIRA/VCR for amendment | NEW PROJECT | Pending | PCR | - | Ravikiran M | [5 empty] | 0
TPFOR automation | NEW PROJECT | Completed | PCR | - | Ravikiran M | EXCEL¦PYTHON | HIGH | 2023-02-02 | - | 90% | 0 | - | - | - | Testing
OOG Workflow Tools | NEW PROJECT | Pending | OPs_Support | Oog Process To Get Approval From The Partner | Viraj B | [5 empty] | 0
India PCR Closer Mail To Be Automated | NEW PROJECT | Pending | PCR | - | Hussain S | [5 empty] | 0
Docs Followup Automation Required (Papua New Guiniea & New Caledonia) | NEW PROJECT | Pending | PCR | - | NavinKumar C | [5 empty] | 0
BAY PLAN Validation RPA | NEW PROJECT | Completed | OPs_Support | - | Mujaffar | EXCEL¦PYTHON | LOW | - | - | 90% | 0 | - | - | - | Testing | -
LARA EDI Automation (Auto click on HARP Insert button) | NEW PROJECT | Completed | DG | - | Sameer S | EXCEL¦PYTHON | MEDIUM | - | - | 90% | 0 | - | - | - | Testing | -
Pre /Post Check Chasers data automation | NEW PROJECT | Pending | Cargo Rediness | - | Paul C | EXCEL¦PYTHON | MEDIUM | - | - |  | 0
0
0
0
0
0
0
0
0
0
0
0

## Project_List Operations_2022 (hidden)
Project_Type | Team | Idea Name | Idea Description | Tools_used | Idea Type | Project Timeline | Start Date | Complete Date | Requester_user | Coding Status | Testing Status | Current Status | Comment | Remarks(Managers Comments) | Benefits achieved
MAINTAINANCE | DG | TAT AUTOMATION _REPORT | - | EXCEL,VBA | Simple | 4-6 Hrs | 2021-12-21 | 2021-12-22 | GOSAVI AMIT | Complete | Complete | Complete |  |  | Time Saving
NEW PROJECT | VGM | VGM AUTOMATION-MISSING VGM CHASER REPORT | DURING CONTIGENCY SITUATION OR VIRA TOOL HAVING ISSUE PRODUCTION OF MISSING CHASER REPORT WILL NOT STOP | PYTHON, EXCEL | Complex | 4-5 days | 2022-04-19 | - | Viraj Tondalkar | Complete | Under Testing | Under Testing |  |  | Time Saving
NEW PROJECT | PCR | WEEKLY REPORT FORMAT & WEEKLY REPORT PPT CREATION | - | EXCEL,VBA | Complex | 6-8 days | 2022-02-25 15:59 | 2022-03-01 21:28 | PRAMOD PATIL | Complete | Complete | Complete |  |  | Time Saving & Accuracy
ENHANCEMENT | CARGO READINESS | CARGO READINESS - CHASING CUSTOMERS | ENHANCE THE EXISTING MACRO AS IT TAKES MORE TIME TO SEND EMAILS TO CUSTOMERS FROM LAPTOP AS COMPARED TO OFFICE DESKTOP | EXCEL,VBA | Simple | 4-6 Hrs | - | - | NIDHEESH LAKSHMANAN | Complete | Complete | Complete |  |  | Time Saving
ENHANCEMENT | DG | IMDG AUDIT FILE 8.35 VERSION_17 28 DEC | - | EXCEL,VBA | Simple | 4-6 Hrs | - | - | SALVI SAMEER | Complete | Complete | Complete |  |  | Accuracy
NEW PROJECT | OPS ASSISTANCE | ANTWERP GATEWAY 1700 | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | 2021-12-23 | 2021-12-25 | LEO RODRIGUES | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | ANTWERP PSA Q913 | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | 2021-12-25 | 2021-12-26 | LEO RODRIGUES | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | ANTWERP PSA TERMINAL 869 | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | 2021-12-26 | 2021-12-28 | LEO RODRIGUES | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | HTTPS://WWW.IAMCONNECTED.EU/ | - | PYTHON, EXCEL | Complex |  | - | - | AMBETH | Pending | Pending | Pending |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | ROTTERDAM WORLD GATEWAY TERMINAL | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | 2021-12-29 | 2021-12-30 | LEO RODRIGUES | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | NETHERLAND DE: EUROGATE | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | 2021-12-31 | 2022-01-04 | LEO RODRIGUES | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | (BREMERHAVEN, DE) CMA3PF | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 4-5 days | 2022-01-05 | 2022-01-12 | LEO RODRIGUES | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | (HAMBURG, DE) BALTIC SHUTTLE SERVICE E | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 4-5 days | 2022-01-12 | 2022-01-19 | LEO RODRIGUES | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | (LUBECK, DE) CONTAINERSHIPS INTRA BALT SERVICE | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | 2022-01-19 | 2022-01-21 | LEO RODRIGUES | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | (WILHELMSHAVEN, DE) BALTIC SHUTTLE SERVICE D | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | 2022-01-22 | 2022-01-22 | LEO RODRIGUES | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | LONDON GATEWAY | - | PYTHON, EXCEL | Complex | 1-2 days | 2022-01-23 | 2022-01-25 | LEO RODRIGUES | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | FELIXSTOWE | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | 2022-01-27 | 2022-01-27 | LEO RODRIGUES | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | SOUTHAMPTON | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | 2022-01-25 | 2022-01-27 | LEO RODRIGUES | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | HTTP://EPORT.SCCTCN.COM/QUERY/VESSELSCHEDULE | - | PYTHON, EXCEL | Complex | 4-5 days | - | - | AMBETH | Pending | Pending | Pending | SHEKOU |  | Time Saving & Accuracy
ENHANCEMENT | DG | RE: DG CARGO AUDIT FILE | - | EXCEL,VBA | Simple | 4-6 Hrs | 2022-01-13 | 2022-01-17 | MANOJ YADAV | Complete | Complete | Complete |  |  | Accuracy
NEW PROJECT | OPS ASSISTANCE | ONE | - | PYTHON, EXCEL | Complex | 1-2 days | 2021-12-22 | 2021-12-24 | LEO RODRIGUES | Complete | Under Testing | Under Testing | PARTNERS VESSELS |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | COSCO | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | 2021-12-24 | 2021-12-28 | LEO RODRIGUES | Complete | Under Testing | Under Testing | PARTNERS VESSELS |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | HAPAG LLOYD | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | 2021-02-02 | 2021-02-03 | LEO RODRIGUES | Complete | Under Testing | Under Testing | PARTNERS VESSELS |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | MAERSK | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | 2021-12-31 | 2022-01-03 | LEO RODRIGUES | Complete | Under Testing | Under Testing | PARTNERS VESSELS |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | CMA CGM | - | PYTHON, EXCEL | Complex | 1-2 days | 2022-01-03 | 2022-01-06 | LEO RODRIGUES | Complete | Under Testing | Under Testing | PARTNERS VESSELS |  | Time Saving & Accuracy
NEW PROJECT | PCR | TRANSHIPMENT_LCR11.1 REPORT_EXCEL FILE CREATION | - | PYTHON, EXCEL | Simple | 3-4 days | 2022-02-01 | 2022-02-04 | SACHIN THAKUR | Complete | Complete | Complete | 1st testing phase completed |  | Time Saving & Accuracy
NEW PROJECT | CARGO READINESS | AUTOMATE EMAIL NOTIFICATION SENT TO CUSTOMERS | AUTOMATICALLY SENDING EMAIL NOTIFICATION TO CUSTOMERS AFTER CANCELLING THE BOOKING. | PYTHON, EXCEL | Complex | 2-3 days | - | - | NIDHEESH LAKSHMANAN | Complete | Complete | Complete |  |  | Time Saving
NEW PROJECT | CARGO READINESS | AUTOMATE JOURNEY LEG RFI EMAILS | AUTOMATE RFI EMAILS SENT TO CARGO CARE TEAM | PYTHON, EXCEL |  | 2-3 days | - | - | NIDHEESH LAKSHMANAN | Complete | Complete | Complete |  |  | Time Saving
NEW PROJECT | CARGO READINESS | IDENTIFY BOOKING PARTY NAME | IDENTIFY BOOKING PARTY NAME FOR BOOKINGS WHERE THE BOOKING PARTY NAME DID NOT GENERATE FROM LARA CARGO | EXCEL,VBA | Simple | 1-2 days | - | - | NIDHEESH LAKSHMANAN | Complete | Complete | Complete |  |  | Time Saving
NEW PROJECT | CARGO READINESS | LARA PML VS TERMINAL LOAD LIST COMPARISON | COMPARE AND PROVIDE OUTPUT IN THE DESIRED FORMAT FOR CHASING CUSTOMERS OR AGENCY WHILE PERFORMING PRE & POST VESSEL CLEAN UP CHECKS | PYTHON, EXCEL | Complex | 2-3 days | - | - | NIDHEESH LAKSHMANAN | Complete | Complete | Complete |  |  | Time Saving
ENHANCEMENT | CARGO READINESS | AUTOMATE EMAIL NOTIFICATION SENT TO CUSTOMERS | HIGHLIGHT THE NOTE SECTION WITH CONTAINER NUMBER PLACE CHANGES. | PYTHON, EXCEL | Simple | 2-3 days | - | - | NIDHEESH LAKSHMANAN | Complete | Complete | Complete |  |  | Time Saving
ENHANCEMENT | CARGO READINESS | LARA PML VS TERMINAL LOAD LIST COMPARISON | NEED TO ADD MORE CRITERIA | PYTHON, EXCEL | Complex | 2-3 days | - | - | NIDHEESH LAKSHMANAN | Complete | Under Testing | Under Testing | AU COMPARISON |  | Time Saving & Accuracy
NEW PROJECT | PCR | SUMMARIZATION OF MONITORING AND SHIPMANAGER COUNT | - | EXCEL,VBA | Simple | 4-6 Hrs | 2022-05-19 | 2022-05-19 | PRAMOD PATIL | Complete | Complete | Complete |  |  | Time Saving & Accuracy
NEW PROJECT | DDSM | Invoice PDF Merger | Automation for merging the multiple pdf into single pdf file | PYTHON, EXCEL | Complex | 2-3 days | - |  | Saddam | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | DDSM | TBI automation | Automation to TBI report (Detention & Demurrage) | PYTHON, EXCEL | Complex | 4-5 days | - |  | Saddam | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | BAY PLANE | BAY PLAN Reminder automation | Start to End auto process throught tool. | EXCEL,VBA,Python | Complex | 4-5 days | - | - | Kishore | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | Outlook mail Sent item details | To get count of mail, being send in days with all specific details. | PYTHON, EXCEL | Complex |  |  |  | Suraj | Pending | Pending | Pending |  |  | Time Saving & Accuracy
NEW PROJECT | PCR | Transhipment process Auto_Missing Voyage | Missing Voyage | PYTHON, EXCEL | Simple | 3-4 days | - | - | SACHIN THAKUR | Complete | Complete | Complete |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | CNC DPS upload | To arrange in orderwise with specific vessel details into excel file. | VBA, Excel | Complex | 3-4 days | - | 2022-11-10 | Rupesh | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | OOG Tracker | - | PYTHON, EXCEL | Complex | 2-3 days | - | - | LEO RODRIGUES | Complete | Complete | Complete |  |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | LTS Creation throught macro. | LTS_Data migration( with multiple condition) from various resources like PDF and excel.. | PYTHON,EXCEL, VBA | Complex | - | - | - | Rupesh | Pending | Pending | Pending |  |  | Time Saving & Accuracy
ENHANCEMENT | OPS ASSISTANCE | COSCO_CMA Comparison | AUTO DATA EXTRACTION FROM WEB SITE THROUGHT TOOL | PYTHON, EXCEL | Complex | 1-2 days | - | - | LEO RODRIGUES | Complete | Under Testing | Under Testing | Comparison |  | Time Saving & Accuracy
NEW PROJECT | OPS ASSISTANCE | Weekly Volume automation | To Collect all simulation and amendment data from sharepoint and collating into common table format | PYTHON, EXCEL | Complex | 1-2 days | - | - | Suraj | Pending | Pending | Pending |  |  | Time Saving & Accuracy
NEW PROJECT | Claim | Request for creating a macro | Get capture the users productivity (In terms of count of mail) on daily basis throught email sent. | EXCEL/VBA | Simple | 5 hrs | 44589 | 44592 | Kumar Manish | Complete | Complete | Complete |  |  | Accuracy
ENHANCEMENT | Claim | Daily Productivity Count | Thank you and would like to confirm that the macro has pulled the data from inbox and is working. However check if it is possible to get the result basis BL no. and date sent against each claim handler. | EXCEL/VBA | Simple | 5 hrs | 44593 | 44593 | Kumar Manish | Complete | Complete | Complete |  |  | Accuracy
ENHANCEMENT | Claim | Daily Productivity Count | Get users email count based on customise date & Fresh¦Old Data along with generic mail box | EXCEL/VBA | Simple | 6 hrs | 44599 | 44601 | Kumar Manish | Complete | Complete | Complete |  |  | Accuracy
NEW PROJECT | OOG -OPS ASSISTANCE | Reminder mail for approval (OOG cargo) | Send mails for approval regarding OOG cargo( with chain mailling) | PYTHON, EXCEL | Complex | 1-2 days | - | - | LEO RODRIGUES | Complete | Complete | Complete |  |  | Time Saving & Accuracy
ENHANCEMENT | Cargo Ops/Transhipment | Transhipment process Auto_Missing Voyage | Need to add first POL in subject line | PYTHON, EXCEL | Simple | 1-2 days | - | - | SACHIN THAKUR | Complete | Complete | Complete |  |  | Time Saving & Accuracy
NEW PROJECT | OOG -OPS ASSISTANCE | reminder process for COD | Sending reminder to partner manually which is time consuming | PYTHON, EXCEL | Complex | 4-5 hrs | - | - | Jessica GOMES | Complete | Complete | Complete |  |  | Time Saving & Accuracy
NEW PROJECT | CARGO READINESS | SERVICE NAME extraction | - | EXCEL/VBA | Simple | 4 hrs | - | - | Deep Tripathi | Complete | Complete | Complete |  |  | Time Saving
NEW PROJECT | DDSM | Extraction of PDF | Extraction of PDF (BL & Invoice) from outlook | PYTHON, EXCEL | Complex | 1-2 days | - | - | Prince | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
MAINTAINANCE | CARGO READINESS | NO activity bug | bug: due to outlook error ( server not find) | EXCEL/VBA | Simple | 4 hrs | - | - | Deep Tripathi | Complete | Complete | Complete |  |  | Time Saving
NEW PROJECT | Cargo Ops/Transhipment | VGM missing _ Transhipment | VGM missing _ Transhipment | PYTHON, EXCEL | Simple | 3-4 days | - | - | SACHIN THAKUR | Complete | Complete | Complete |  |  | Time Saving & Accuracy
NEW PROJECT | DG | Cxml to xlsx and comparision | Cxml to xlsx and comparision with Harp | PYTHON, EXCEL | Simple | 1-2 days | - | - | MANOJ YADAV | Complete | Under Testing | Under Testing |  |  | Time Saving & Accuracy
NEW PROJECT | VGM | Edi_001 automation | Edi_001 automation | PYTHON, EXCEL | Complex | 4-5 days | 44853 | - | Viraj Tondalkar | Complete | Under Testing | Under Testing |  |  | Time Saving
ENHANCEMENT | Cargo Ops/Transhipment | VGM missing _ Transhipment | Added code for column title and duplicate container having 1 VGM number, missing for second container | PYTHON, EXCEL | Simple | 1-2 days | - | - | SACHIN THAKUR | Complete | Complete | Complete |  |  | Time Saving & Accuracy
NEW PROJECT | CARGO READINESS | Cargo Readiness - Automation of NDNL Cancellation Process | Automate the entire process( data process + mail distributing to Bot) | PYTHON, EXCEL | Simple | 2-3 days | - | - | Deep Tripathi | Complete | Under Testing | Under Testing |  |  | Time Saving
NEW PROJECT | Cargo Ops/Transhipment | VGM missing _ Transhipment_06 & 11.0 | VGM missing _ Transhipment_06 & 11.0 | PYTHON, EXCEL | Simple | 3-4 days | - | - | SACHIN THAKUR | Complete | Complete | Complete |  |  | Time Saving & Accuracy
NEW PROJECT | DG | Scanned PDF to be converted into an editable | Scanned PDF to be converted into an editable | PYTHON, EXCEL | Simple | 1-2 days | - | - | SALVI SAMEER | Complete | Complete | Complete |  |  | Time Saving & Accuracy
NEW PROJECT | PCR | INDIA PCR CLOSER MAIL TO BE AUTOMATED | INDIA PCR CLOSER MAIL TO BE AUTOMATED | PYTHON, EXCEL | Complex | 4-5 days | - | - | SHAIKH Hussain | Pending | Pending | Pending

## Project_List Others Dept_2022 (hidden)
Project_Type | Team | Idea Name | Idea Description | Tools_used | Idea Type | Project Timeline | Start Date | Complete Date | Requester_user | Coding Status | Testing Status | Status | Remarks(Managers Comments) | Benefits achieved
to be updated by delivery Team | to be updated by delivery Team | to be updated by delivery Team | to be updated by delivery Team | to be updated by Akhilesh | to be updated by Akhilesh | to be updated by Akhilesh | to be updated by Akhilesh | to be updated by Akhilesh | to be updated by delivery team | to be updated by Akhilesh | to be updated by Akhilesh | to be updated by Akhilesh | to be updated by delivery team | to be updated by delivery team
ENHANCEMENT | SVC_ | Daily Count : With Audit status | - | EXCEL/VBA | Simple | 5 hrs | 2021-12-21 | 2021-12-22 | Arun Mukannath | Complete | Complete | Complete |  | Time Saving & Accuracy
NEW PROJECT | IT team Thane | Auto extract console data and pull screen shot of command prompt | Auto extract console data and pull screen shot of command prompt | Python¦BAT | Complex | 5 hrs | 2022-02-15 | 2022-02-15 | Neeraj Jha | Complete | Complete | Complete |  | Time Saving
NEW PROJECT | SVC_ | To Extract the SVC contract details from LARA Mirror | Based on Contract number and Amendment number , get entire details `` | ExCEL/VBA | Simple | 4.30 hrs | 2022-02-16 | 2022-02-16 | Preetam M | Complete | Complete | Complete |  | Time Saving & Accuracy
ENHANCEMENT | SVC_ | Port Group extraction | Additionally, extract Ports of respective groups | ExCEL/VBA | Simple | 5 hrs | 2022-02-16 | 2022-02-16 | Preetam M | Complete | Complete | Complete |  | Time Saving & Accuracy
NEW PROJECT | Tender_Integration | Merge, Dry, Reefer D & D Consolidation | - | ExCEL/VBA | Complex | 3-4 Days | 2022-03-08 | 2022-03-15 | Navid M | Complete | Complete | Complete |  | Time Saving & Accuracy
NEW PROJECT | HR_Photo_dist. | Dist. Official photo to resp. emplyee | - | Python¦Excel | Complex | 3-4 Days | 2022-06-12 | 2022-07-21 | Savio Johanathan | Complete | Complete | Complete |  | Time Saving & Accuracy
ENHANCEMENT | SVC_ | Qspot mail template | - | ExCEL/VBA | Simple | 5 hrs | 2022-06-24 | 2022-06-24 | Preetam M | Complete | Complete | Complete |  | Time Saving & Accuracy
ENHANCEMENT | SVC_ | DDSM_column addition | - | ExCEL/VBA | Simple | 5 hrs | 2022-06-24 | 2022-06-24 | Preetam M | Complete | Complete | Complete |  | Time Saving & Accuracy
NEW PROJECT | Tender | Consolidation of multiple appendix tabs | consolidation of appendix data with charges | ExCEL/VBA | Simple | 5 hrs | - | - | Arvind / Lokesh | Complete | Work In Progrees | Work In Progrees |  | Time Saving & Accuracy
NEW PROJECT | Booking Team | Email notification with different type of template & LARA details extraction | Auto extract details from LARA and send notification basis on different different type of template | Python¦ExCEL/VBA | Simple | 10-14 days | - | - | Balaganesh | Complete | Complete | Complete |  | Time Saving & Accuracy